## Dependency Rules
rule_id | repair_type | depends_on_repair_type | dependency_type | critical_path_flag | review_status | decision_reference | source_reference | version
1 | Roof replacement / major repair |  |  |  | pending |  |  | 1
2 | Foundation crack repair |  |  |  | pending |  |  | 1
3 | Active water intrusion / leak |  |  |  | pending |  |  | 1
4 | Mold remediation | Active water intrusion / leak, Broken plumbing active, Roof replacement / major repair | hard | TRUE | pending | D-V11-003 | ANSI/IICRC S520 Standard for Professional Mold Remediation | 1
5 | Knob-and-tube wiring replacement |  |  |  | pending |  |  | 1
6 | Failed HVAC replacement |  |  |  | pending |  |  | 1
7 | Broken plumbing active |  |  |  | pending |  |  | 1
8 | Electrical panel upgrade |  |  |  | pending |  |  | 1
9 | Septic / sewer line failure |  |  |  | pending |  |  | 1
10 | Caulking / weatherstripping |  |  |  | pending |  |  | 1
11 | Gutter repair / replacement | Roof replacement / major repair | hard | TRUE | pending | D-V11-003 | IRC roofing requirements - gutters must integrate with drip edge | 1
12 | Peeling exterior paint |  |  |  | pending |  |  | 1
13 | Non-functional minor systems |  |  |  | pending |  |  | 1
14 | HVAC filter / tune-up |  |  |  | pending |  |  | 1
15 | Worn deck / porch boards |  |  |  | pending |  |  | 1
16 | Cracked driveway / walkway |  |  |  | pending |  |  | 1
17 | Window seal failure |  |  |  | pending |  |  | 1
18 | Interior paint | Active water intrusion / leak, Flooring refinish or replacement | hard | TRUE | pending | D-V11-003 | NAHB moisture guidelines; NAHB schedule template | 1
19 | Flooring refinish or replacement | Active water intrusion / leak | hard | TRUE | pending | D-V11-003 | NAHB Model Green Home Building Guidelines moisture testing requirement | 1
20 | Kitchen cabinet hardware update |  |  |  | pending |  |  | 1
21 | Fixture replacement | Broken plumbing active, Failed HVAC replacement, Knob-and-tube wiring replacement, Electrical panel upgrade | hard | TRUE | pending | D-V11-003 | IRC R109.1.2 rough inspection required before fixture installation | 1
22 | Landscaping / curb appeal | Septic / sewer line failure | hard | TRUE | pending | D-V11-003 | NAHB Land Development Checklist - subterranean utilities before surface landscaping | 1
23 | Deep cleaning / declutter | Roof replacement / major repair, Flooring refinish or replacement, Interior paint, Mold remediation, Knob-and-tube wiring replacement, Failed HVAC replacement, Broken plumbing active, Bathroom cosmetic refresh | hard | TRUE | pending | D-V11-003 | NAHB residential construction timeline - cleaning is final step | 1
24 | Professional staging |  |  |  | pending |  |  | 1
25 | Professional photography |  |  |  | pending |  |  | 1
26 | Bathroom cosmetic refresh | Active water intrusion / leak, Broken plumbing active | hard | TRUE | pending | D-V11-003 | Bathroom remodel sequencing - moisture source must be resolved first | 1
27 | Closet organization |  |  |  | pending |  |  | 1
28 | Garage door repair or replacement |  |  |  | pending |  |  | 1
29 | Attic insulation | Knob-and-tube wiring replacement, Roof replacement / major repair | hard | TRUE | pending | D-V11-003 | NEC 394.12 prohibits insulation over knob-and-tube wiring; IRC dried-in requirement | 1
30 | Accessibility improvements |  |  |  | pending |  |  | 1
31 | Exterior access modifications |  |  |  | pending |  |  | 1

## Duration Lead Time Rules
rule_id | repair_type | duration_low_days | duration_high_days | lead_time_low_days | lead_time_high_days | review_status | decision_reference | legacy_source_reference | source_name | source_url | access_date | source_excerpt | review_notes | version
1 | Roof replacement / major repair | 1 | 14 | 7 | 21 | pending | D-V11-003 | https://www.angi.com/articles/how-long-replace-roof.htm | Angi | https://www.angi.com/articles/how-long-replace-roof.htm |  |  |  | 1
2 | Foundation crack repair | 1 | 21 | 3 | 14 | pending | D-V11-003 | https://www.angi.com/articles/how-long-foundation-repair-takes.htm | Angi | https://www.angi.com/articles/how-long-foundation-repair-takes.htm |  |  |  | 1
3 | Active water intrusion / leak | 0.25 | 3 | 1 | 5 | pending | D-V11-003 | https://www.angi.com/articles/cost-to-repair-leaking-pipe.htm | Angi | https://www.angi.com/articles/cost-to-repair-leaking-pipe.htm |  |  |  | 1
4 | Mold remediation | 1 | 21 | 3 | 10 | pending | D-V11-003 | https://www.angi.com/companylist/mold-testing-and-remediation.htm | Angi | https://www.angi.com/companylist/mold-testing-and-remediation.htm |  |  |  | 1
5 | Knob-and-tube wiring replacement | 3 | 10 | 7 | 21 | pending | D-V11-003 | https://www.angi.com/articles/how-long-rewire-house.htm | Angi | https://www.angi.com/articles/how-long-rewire-house.htm |  |  |  | 1
6 | Failed HVAC replacement | 0.5 | 5 | 3 | 14 | pending | D-V11-003 | https://www.angi.com/articles/insider-s-price-guide-new-heating-and-cooling-system.htm | Angi | https://www.angi.com/articles/insider-s-price-guide-new-heating-and-cooling-system.htm |  |  |  | 1
7 | Broken plumbing active | 0.13 | 3 | 1 | 5 | pending | D-V11-003 | https://www.homeadvisor.com/cost/plumbing/slab-leak-repair/ | HomeAdvisor | https://www.homeadvisor.com/cost/plumbing/slab-leak-repair/ |  |  |  | 1
8 | Electrical panel upgrade | 0.5 | 4 | 7 | 21 | pending | D-V11-003 | https://www.homeadvisor.com/cost/electrical/upgrade-an-electrical-panel/ | HomeAdvisor | https://www.homeadvisor.com/cost/electrical/upgrade-an-electrical-panel/ |  |  |  | 1
9 | Septic / sewer line failure | 1 | 56 | 5 | 14 | pending | D-V11-003 | https://www.angi.com/articles/how-long-septic-replacement.htm | Angi | https://www.angi.com/articles/how-long-septic-replacement.htm |  |  |  | 1
10 | Caulking / weatherstripping | 0.25 | 1 | 0 | 2 | estimated | D-V11-003 | No single-source duration baseline available. Labor duration defies daily metric per source analysis. | No single-source baseline |  |  |  | No single-source duration baseline available. Labor duration defies daily metric per source analysis. | 1
11 | Gutter repair / replacement | 0.13 | 7 | 3 | 10 | pending | D-V11-003 | https://www.angi.com/companylist/us/mi/dearborn/gutter-repair-replacement.htm | Angi | https://www.angi.com/companylist/us/mi/dearborn/gutter-repair-replacement.htm |  |  |  | 1
12 | Peeling exterior paint | 3 | 6 | 3 | 14 | pending | D-V11-003 | https://www.homeadvisor.com/cost/painting/paint-a-home-exterior/ | HomeAdvisor | https://www.homeadvisor.com/cost/painting/paint-a-home-exterior/ |  |  |  | 1
13 | Non-functional minor systems | 0.5 | 2 | 1 | 7 | estimated | D-V11-003 | No single-source duration baseline available. Scope varies by system type. Requires GC review. | No single-source baseline |  |  |  | No single-source duration baseline available. Scope varies by system type. Requires GC review. | 1
14 | HVAC filter / tune-up | 0.125 | 0.25 | 1 | 5 | estimated | D-V11-003 | No single-source duration baseline available. 1-2 hours typical but varies by service agreement. | No single-source baseline |  |  |  | No single-source duration baseline available. 1-2 hours typical but varies by service agreement. | 1
15 | Worn deck / porch boards | 1 | 5 | 3 | 14 | estimated | D-V11-003 | No single-source duration baseline available. Board count dependent. Requires GC review. | No single-source baseline |  |  |  | No single-source duration baseline available. Board count dependent. Requires GC review. | 1
16 | Cracked driveway / walkway | 1 | 3 | 3 | 10 | estimated | D-V11-003 | No single-source duration baseline available. Cure time adds days. Requires GC review. | No single-source baseline |  |  |  | No single-source duration baseline available. Cure time adds days. Requires GC review. | 1
17 | Window seal failure | 0.5 | 2 | 7 | 21 | estimated | D-V11-003 | No single-source duration baseline available. Glass unit order lead time drives range. | No single-source baseline |  |  |  | No single-source duration baseline available. Glass unit order lead time drives range. | 1
18 | Interior paint | 0.25 | 3 | 3 | 10 | pending | D-V11-003 | https://www.angi.com/articles/how-long-does-it-take-to-paint-a-room.htm | Angi | https://www.angi.com/articles/how-long-does-it-take-to-paint-a-room.htm |  |  |  | 1
19 | Flooring refinish or replacement | 3 | 5 | 3 | 14 | pending | D-V11-003 | https://www.angi.com/articles/how-long-does-refinishing-hardwood-floors-take.htm | Angi | https://www.angi.com/articles/how-long-does-refinishing-hardwood-floors-take.htm |  |  |  | 1
20 | Kitchen cabinet hardware update | 0.25 | 1 | 2 | 7 | estimated | D-V11-003 | No single-source duration baseline available. Hardware shipping dependent. | No single-source baseline |  |  |  | No single-source duration baseline available. Hardware shipping dependent. | 1
21 | Fixture replacement | 0.25 | 1 | 1 | 7 | estimated | D-V11-003 | No single-source duration baseline available. Conditional on plumbing scope. | No single-source baseline |  |  |  | No single-source duration baseline available. Conditional on plumbing scope. | 1
22 | Landscaping / curb appeal | 1 | 5 | 1 | 7 | estimated | D-V11-003 | No single-source duration baseline available. Scope-dependent. | No single-source baseline |  |  |  | No single-source duration baseline available. Scope-dependent. | 1
23 | Deep cleaning / declutter | 0.5 | 1.25 | 0 | 3 | pending | D-V11-003 | https://www.angi.com/articles/how-long-deep-clean-house.htm | Angi | https://www.angi.com/articles/how-long-deep-clean-house.htm |  |  |  | 1
24 | Professional staging | 0.5 | 1 | 7 | 21 | estimated | D-V11-003 | No single-source duration baseline available. Stager availability varies by market. Anomaly rule ANOM-STAGING-UNDER-21-DAYS applies. | No single-source baseline |  |  |  | No single-source duration baseline available. Stager availability varies by market. Anomaly rule ANOM-STAGING-UNDER-21-DAYS applies. | 1
25 | Professional photography | 0.25 | 0.5 | 3 | 14 | estimated | D-V11-003 | No single-source duration baseline available. 2-4 hour shoot typical. | No single-source baseline |  |  |  | No single-source duration baseline available. 2-4 hour shoot typical. | 1
26 | Bathroom cosmetic refresh | 1 | 28 | 5 | 14 | pending | D-V11-003 | https://www.homeadvisor.com/cost/bathrooms/shower-remodel/ | HomeAdvisor | https://www.homeadvisor.com/cost/bathrooms/shower-remodel/ |  |  |  | 1
27 | Closet organization | 0.5 | 2 | 3 | 14 | estimated | D-V11-003 | No single-source duration baseline available. Custom systems add lead time. | No single-source baseline |  |  |  | No single-source duration baseline available. Custom systems add lead time. | 1
28 | Garage door repair or replacement | 0.5 | 3 | 1 | 7 | pending | D-V11-003 | https://www.homeadvisor.com/cost/garages/install-a-garage-door/ | HomeAdvisor | https://www.homeadvisor.com/cost/garages/install-a-garage-door/ |  |  |  | 1
29 | Attic insulation | 0.5 | 3 | 3 | 10 | pending | D-V11-003 | https://www.angi.com/articles/should-i-remove-old-insulation-when-i-upgrade.htm | Angi | https://www.angi.com/articles/should-i-remove-old-insulation-when-i-upgrade.htm |  |  |  | 1
30 | Minor accessibility improvements | 1 | 3 | 7 | 14 | pending | D-V11-001 | Angi/HomeAdvisor published ranges (accessed 2026-05) | Angi/HomeAdvisor |  |  |  | Angi/HomeAdvisor published ranges (accessed 2026-05) | 1
31 | Exterior access modifications | 2 | 5 | 14 | 21 | pending | D-V11-001 | Angi/HomeAdvisor published ranges (accessed 2026-05) | Angi/HomeAdvisor |  |  |  | Angi/HomeAdvisor published ranges (accessed 2026-05) | 1